## START HERE
VERTEX STRATEGIC FINANCE
Contractor KPI Scorecard
Understand the financial drivers behind your jobs, margins, cash flow and business performance.
What This Scorecard Does
This scorecard helps owner-led contractors and trades businesses see the financial position of the work they are already doing. It is a financial management and decision-support tool — not an accounting system, an estimating system, a project-management platform or an industry benchmarking report.
— Track financial performance month over month
— Understand gross profit and gross margin
— Monitor major direct-cost categories
— Compare estimated and actual job profitability
— Monitor accounts receivable, accounts payable and cash
— Understand backlog and job activity
— Compare results against your own targets
— Identify areas worth investigating
How to Use It
1. Enter monthly financial and operational data. (MONTHLY INPUTS tab)
2. Enter recent or active job performance. (JOB PERFORMANCE tab)
3. Set your own KPI targets. (KPI TARGETS tab)
4. Review KPI trends and working capital. (KPI ANALYSIS and WORKING CAPITAL tabs)
5. Identify the questions worth investigating. (ACTION PLAN and EXECUTIVE DASHBOARD tabs)
Enter 0 when a required category legitimately has no activity. Leave a required input blank only when the information has not yet been entered. Blank required inputs are treated as incomplete information, not zero.
Targets in this workbook are user-defined planning goals, not industry benchmarks or recommendations. This scorecard uses user-defined targets and does not provide contractor-industry benchmarks.
All sample data is fictional and provided for demonstration purposes only. Replace every figure with your own information.
Reading the Workbook
| Input | Shaded cells are yours to change. Type over the example figures with your own.
| Formula | Unshaded cells calculate automatically. Sheets are protected without a password — use Review › Unprotect Sheet if you need to edit them.
| Incomplete Inputs | A figure the calculation needs has not been entered. A blank cell means not entered; it is never treated as zero. Enter 0 where the real answer is zero.
| Incomplete Job Inputs | One or more job rows have some information entered but not all of it. Affected job totals and rankings are withheld until those rows are completed or cleared.
| N/M | Not meaningful — the figures entered leave the measure undefined, such as a margin on revenue of zero.
| Set Target | The target this comparison needs has not been entered on the KPI TARGETS tab.
| Context Dependent | There is no universally correct direction for this measure. It is reported, not scored.
| Monitor | Worth watching in the context of your own capacity, pipeline and plans.
Definitions
| Term | What it means
| Gross Profit | Revenue less the direct job costs entered in this workbook.
| Gross Margin % | Gross Profit divided by Revenue.
| Operating Profit | Gross Profit less the operating and overhead costs entered here. It is not net income: it excludes items this scorecard does not capture, among them depreciation, interest and taxes.
| Owner Draws / Distributions | Distributions to owners. They are not operating expenses and do not reduce operating profit. They are entered separately and never deducted from gross profit or operating profit.
| Backlog | Contracted work not yet recognised as revenue, based on the amount you enter. Backlog is not cash, and it is not guaranteed future profit.
| Cost Variance | Actual or current direct job cost less estimated direct job cost. A positive variance means costs are above estimate; a negative variance means costs are below estimate.
| Margin Variance | Actual or current gross margin % less estimated gross margin %, expressed in percentage points. Positive means margin above estimate; negative means margin below estimate.
| Approximate A/R Days | Accounts receivable divided by revenue for the reporting month, multiplied by 30.4 days. An approximation from a single month, not a rolling average.
| Cash Coverage | Ending cash divided by total operating cost for the reporting month — direct job costs plus overhead. Expressed in months.
| Current Ratio | Current assets divided by current liabilities, as entered.
Important. This resource is provided for general informational and planning purposes only and does not constitute accounting, tax, legal, construction-law, investment or financial advice, and no assurance of any kind is provided. This workbook does not perform percentage-of-completion accounting, work-in-progress accounting or revenue recognition, and it does not model statutory holdback or retainage requirements, which vary by jurisdiction and circumstance. Results for jobs in progress are based only on the costs entered and may change. Nothing here is a professional opinion on the financial condition or performance of any business.
Vertex Strategic Finance
CPA-Led Accounting & Advisory for Owner-Led Businesses
www.vertexstrategicfinance.ca ¦ info@vertexstrategicfinance.ca

## MONTHLY INPUTS
VERTEX STRATEGIC FINANCE
Monthly Inputs | [5 empty] | FICTIONAL EXAMPLE DATA — FOR DEMONSTRATION ONLY
Twelve months of financial and operating data. Everything else in this workbook is calculated from this tab.
Shaded cells are yours to fill in. Enter 0 when a required category legitimately had no activity in that month. Leave a required cell blank only when the information has not yet been entered — a blank is treated as missing information, never as zero.
REPORTING PERIOD
| Business Name | Northfield Contracting Ltd. — Fictional Example
| Reporting Period Label | Fiscal Year 2025
| Reporting Month (enter 1 – 12) | 12 | Reporting month: Dec 2025 Marked complete. Profitability inputs: complete.
MONTH SETUP
| Month Label | Jan 2025 | Feb 2025 | Mar 2025 | Apr 2025 | May 2025 | Jun 2025 | Jul 2025 | Aug 2025 | Sep 2025 | Oct 2025 | Nov 2025 | Dec 2025
| Month Completed? (Yes / No) | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
A month is available for reporting when you mark it Yes. A completed month with no revenue is legitimate and is reported as zero revenue, not as missing information.
REVENUE REQUIRED FOR PROFITABILITY
| Line item | Jan 2025 | Feb 2025 | Mar 2025 | Apr 2025 | May 2025 | Jun 2025 | Jul 2025 | Aug 2025 | Sep 2025 | Oct 2025 | Nov 2025 | Dec 2025
| Contract / Project Revenue | 380000 | 355000 | 430000 | 505000 | 585000 | 640000 | 690000 | 665000 | 610000 | 560000 | 495000 | 445000
| Service / Maintenance Revenue | 62000 | 58000 | 66000 | 71000 | 78000 | 82000 | 85000 | 84000 | 80000 | 76000 | 70000 | 68000
| Other Operating Revenue | 4500 | 3800 | 5200 | 6100 | 7400 | 8200 | 8800 | 8100 | 7600 | 6900 | 5800 | 5100
| Total Revenue | 446500 | 416800 | 501200 | 582100 | 670400 | 730200 | 783800 | 757100 | 697600 | 642900 | 570800 | 518100
DIRECT JOB COSTS REQUIRED FOR PROFITABILITY
| Line item | Jan 2025 | Feb 2025 | Mar 2025 | Apr 2025 | May 2025 | Jun 2025 | Jul 2025 | Aug 2025 | Sep 2025 | Oct 2025 | Nov 2025 | Dec 2025
| Direct Labour | 102700 | 97300 | 115300 | 132900 | 152000 | 164700 | 176300 | 171500 | 159400 | 147400 | 131600 | 119700
| Subcontractors | 116600 | 108800 | 134900 | 162300 | 193800 | 219700 | 243200 | 226100 | 200000 | 177800 | 152200 | 135100
| Materials | 89800 | 84800 | 101700 | 119100 | 138400 | 152500 | 164900 | 158300 | 144700 | 132100 | 116200 | 104700
| Equipment / Rentals | 12600 | 11500 | 15100 | 18700 | 22500 | 25500 | 28400 | 25800 | 22200 | 19600 | 16300 | 14600
| Permits / Direct Project Fees | 4600 | 4400 | 5300 | 6200 | 7800 | 8700 | 9500 | 9000 | 7600 | 6900 | 6000 | 5400
| Other Direct Job Costs | 5000 | 5000 | 5700 | 6700 | 7800 | 8700 | 9500 | 9000 | 8100 | 7400 | 6400 | 5400
| Total Direct Job Costs | 331300 | 311800 | 378000 | 445900 | 522300 | 579800 | 631800 | 599700 | 542000 | 491200 | 428700 | 384900
| Gross Profit | 115200 | 105000 | 123200 | 136200 | 148100 | 150400 | 152000 | 157400 | 155600 | 151700 | 142100 | 133200
| Gross Margin % | 25.8% | 25.19% | 24.58% | 23.4% | 22.09% | 20.6% | 19.39% | 20.79% | 22.31% | 23.6% | 24.89% | 25.71%
Gross Profit is Total Revenue less Total Direct Job Costs as entered here. Where revenue is zero, Gross Margin % reads N/M because the measure is undefined.
OPERATING / OVERHEAD COSTS REQUIRED FOR OPERATING PROFIT
| Line item | Jan 2025 | Feb 2025 | Mar 2025 | Apr 2025 | May 2025 | Jun 2025 | Jul 2025 | Aug 2025 | Sep 2025 | Oct 2025 | Nov 2025 | Dec 2025
| Administrative Payroll | 58000 | 58000 | 59500 | 59500 | 61000 | 61000 | 62500 | 62500 | 62500 | 61000 | 61000 | 61000
| Rent / Occupancy | 9800 | 9800 | 9800 | 9800 | 9800 | 9800 | 9800 | 9800 | 9800 | 9800 | 9800 | 9800
| Vehicles / Fleet | 12400 | 11800 | 13200 | 14100 | 15300 | 16200 | 16800 | 16100 | 15200 | 14300 | 13100 | 12600
| Insurance | 6900 | 6900 | 6900 | 7250 | 7250 | 7250 | 7250 | 7250 | 7250 | 7250 | 7250 | 7250
| Software / Subscriptions | 2150 | 2150 | 2150 | 2280 | 2280 | 2280 | 2280 | 2280 | 2380 | 2380 | 2380 | 2380
| Marketing | 4200 | 3600 | 5100 | 6300 | 7200 | 7800 | 7500 | 6900 | 6100 | 5400 | 4800 | 5600
| Professional Fees | 3400 | 9200 | 3400 | 3400 | 3400 | 3400 | 3400 | 3400 | 3400 | 3400 | 3400 | 7800
| Office / Administrative | 2900 | 2750 | 3100 | 3300 | 3450 | 3600 | 3700 | 3550 | 3350 | 3200 | 3000 | 3050
| Other Overhead | 1800 | 1650 | 1900 | 2050 | 2200 | 2350 | 2450 | 2300 | 2150 | 2000 | 1850 | 1900
| Total Operating / Overhead Costs | 101550 | 105850 | 105050 | 107980 | 111880 | 113680 | 115680 | 114080 | 112130 | 108730 | 106580 | 111380
| Operating Profit | 13650 | -850 | 18150 | 28220 | 36220 | 36720 | 36320 | 43320 | 43470 | 42970 | 35520 | 21820
| Operating Margin % | 3.057% | -0.2039% | 3.621% | 4.848% | 5.403% | 5.029% | 4.634% | 5.722% | 6.231% | 6.684% | 6.223% | 4.212%
Operating Profit is Gross Profit less the overhead entered above. It is not net income — it excludes items this scorecard does not capture, among them depreciation, interest and taxes.
OWNER DISTRIBUTIONS NOT AN OPERATING EXPENSE
| Line item | Jan 2025 | Feb 2025 | Mar 2025 | Apr 2025 | May 2025 | Jun 2025 | Jul 2025 | Aug 2025 | Sep 2025 | Oct 2025 | Nov 2025 | Dec 2025
| Owner Draws / Distributions | 18000 | 18000 | 18000 | 22000 | 22000 | 28000 | 32000 | 28000 | 25000 | 22000 | 20000 | 35000
| Operating Profit Less Owner Distributions | -4350 | -18850 | 150 | 6220 | 14220 | 8720 | 4320 | 15320 | 18470 | 20970 | 15520 | -13180
Owner draws and distributions are not operating expenses and do not reduce accounting operating profit. They are entered here only so the line below can be shown. Operating Profit Less Owner Distributions is a planning measure — it is not profit and it is not cash flow.
CASH AND WORKING CAPITAL
| Line item | Jan 2025 | Feb 2025 | Mar 2025 | Apr 2025 | May 2025 | Jun 2025 | Jul 2025 | Aug 2025 | Sep 2025 | Oct 2025 | Nov 2025 | Dec 2025
| Ending Cash | 248000 | 226000 | 214000 | 209000 | 198000 | 221000 | 256000 | 312000 | 368000 | 421000 | 458000 | 487000
| Accounts Receivable | 764000 | 740000 | 940000 | 1168000 | 1411000 | 1633000 | 1831000 | 1718000 | 1469000 | 1248000 | 1033000 | 903000
| Accounts Payable | 397000 | 385000 | 489000 | 607000 | 734000 | 849000 | 952000 | 893000 | 764000 | 649000 | 537000 | 470000
| Current Assets | 1054000 | 1004000 | 1200000 | 1430000 | 1670000 | 1920000 | 2156000 | 2094000 | 1895000 | 1721000 | 1537000 | 1433000
| Current Liabilities | 715000 | 691000 | 821000 | 975000 | 1132000 | 1273000 | 1393000 | 1321000 | 1165000 | 1023000 | 883000 | 801000
Current Assets and Current Liabilities should be the totals from your balance sheet, including the cash, receivables and payables entered above.
OPERATING ACTIVITY
| Line item | Jan 2025 | Feb 2025 | Mar 2025 | Apr 2025 | May 2025 | Jun 2025 | Jul 2025 | Aug 2025 | Sep 2025 | Oct 2025 | Nov 2025 | Dec 2025
| Jobs Started | 4 | 3 | 5 | 6 | 7 | 7 | 8 | 6 | 5 | 5 | 4 | 4
| Jobs Completed | 3 | 4 | 4 | 5 | 6 | 7 | 7 | 7 | 6 | 5 | 5 | 4
| Jobs in Progress at Month End | 7 | 6 | 7 | 8 | 9 | 9 | 10 | 9 | 8 | 8 | 7 | 7
| Backlog (contracted work not yet revenue) | 1420000 | 1365000 | 1510000 | 1685000 | 1840000 | 1915000 | 1880000 | 1760000 | 1615000 | 1520000 | 1445000 | 1595000
| Approved Change Orders | 18500 | 9200 | 26400 | 31800 | 44700 | 52300 | 38900 | 27600 | 19800 | 23400 | 14600 | 41200
| Quotes / Estimates Issued (optional) | 9 | 7 | 11 | 13 | 15 | 16 | 14 | 12 | 11 | 10 | 8 | 9
| Quotes / Estimates Won (optional) | 4 | 3 | 5 | 6 | 7 | 7 | 6 | 5 | 5 | 4 | 3 | 4
Quotes issued and quotes won are optional. Leaving them blank does not block any other calculation in this workbook; quote conversion simply reports N/M. Backlog is contracted work not yet recognised as revenue — it is not cash and not guaranteed profit.
MONTH INPUT STATUS
| Input group | Jan 2025 | Feb 2025 | Mar 2025 | Apr 2025 | May 2025 | Jun 2025 | Jul 2025 | Aug 2025 | Sep 2025 | Oct 2025 | Nov 2025 | Dec 2025
| Revenue Inputs | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
| Direct Job Cost Inputs | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
| Overhead Inputs | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
| Cash / Working Capital Inputs | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
| Profitability Assessment | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
Profitability Assessment is complete only when all three revenue lines, all six direct job cost lines and all nine overhead lines are entered for that month. Until then the workbook reports Incomplete Inputs rather than an artificially favourable result.
Vertex Strategic Finance ¦ FICTIONAL EXAMPLE DATA — FOR DEMONSTRATION ONLY. Replace every figure above with your own information.
Completeness flags used across the workbook
| revenue ok | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| direct ok | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| overhead ok | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| gross ok | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| profit ok | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| working capital ok | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| month marked complete | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| reporting month valid | 1
| reporting month marked complete | 1
| prior month marked complete | 1
| provisional months in the KPI trend | 0
| contributes to the KPI trend block | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| contributes to the working capital trend | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| contributes to dashboard chart 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| contributes to dashboard chart 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| provisional months in the working capital trend | 0
| provisional months in chart 1 | 0
| provisional months in chart 2 | 0
| prior-month comparison exists but prior month is incomplete | 0

## JOB PERFORMANCE
VERTEX STRATEGIC FINANCE
Job Performance | [6 empty] | FICTIONAL EXAMPLE DATA — FOR DEMONSTRATION ONLY
Up to ten recent or active jobs — estimated against actual or current direct costs.
Enter each job on its own row. A job is included once all of its required fields are entered — name, status, contract value, approved change orders and all four estimated and all four actual or current cost lines. Enter 0 where a cost line is genuinely zero. A row left entirely blank is ignored; a row with some information but not all is marked Incomplete and the job totals below are withheld until it is completed or cleared.
JOB INPUTS
|  |  | CONTRACT VALUE |  |  | ESTIMATED DIRECT COSTS |  |  |  |  | ACTUAL / CURRENT DIRECT COSTS | [5 empty] | any partial / complete count / completed count
| Job / Project Name | Status | Original Contract | Approved Change Orders | Revised Contract | Est. Direct Labour | Est. Sub-contractor | Est. Material | Est. Equipment / Other | Est. Total Direct Cost | Act. Direct Labour | Act. Sub-contractor | Act. Material | Act. Equipment / Other | Act. / Current Total Cost | row state 1=complete 0=empty 2=partial | 0 | completed job flag
| Harbourview Retail Fit-Out | Complete | 485000 | 32000 | 517000 | 112000 | 148000 | 122000 | 16000 | 398000 | 118500 | 151000 | 131000 | 17500 | 418000 | 1 | 6 | 1 | 517000 | 20000 | -0.038686 | Harbourview Retail Fit-Out | 23.02% | 19.15%
| Cedar Ridge Multi-Unit Renovation | Complete | 862000 | 48500 | 910500 | 196000 | 268000 | 214000 | 28000 | 706000 | 188000 | 259500 | 206000 | 25500 | 679000 | 1 | 4 | 1 | 910500 | -27000 | 0.029653 | Cedar Ridge Multi-Unit Renovation | 22.46% | 25.43%
| Riverbend Warehouse Expansion | In Progress | 1240000 | 76000 | 1316000 | 284000 | 392000 | 306000 | 42000 | 1024000 | 231000 | 318000 | 268000 | 34500 | 851500 | 1 |  | 0 | 1316000
| Northgate Roof Replacement | Complete | 168000 | 0 | 168000 | 42000 | 38000 | 46000 | 6500 | 132500 | 44800 | 41500 | 49200 | 7200 | 142700 | 1 |  | 1 | 168000 | 10200 | -0.060716 | Northgate Roof Replacement | 21.13% | 15.06%
| Willowbrook Tenant Improvements | Complete | 342000 | 18900 | 360900 | 78000 | 96000 | 82000 | 11000 | 267000 | 74500 | 91000 | 79500 | 9800 | 254800 | 1 |  | 1 | 360900 | -12200 | 0.033803 | Willowbrook Tenant Improvements | 26.02% | 29.4%
| Sunnyside Mechanical Upgrade | In Progress | 596000 | 0 | 596000 | 138000 | 182000 | 148000 | 19000 | 487000 | 96000 | 121000 | 104000 | 12500 | 333500 | 1 |  | 0 | 596000
[16 empty] | 0 |  | 0
[16 empty] | 0 |  | 0
[16 empty] | 0 |  | 0
[16 empty] | 0 |  | 0
Revised Contract Value is Original Contract Value plus Approved Change Orders. Only approved change orders should be included — potential or unapproved change orders do not belong in contract value. Status must read Complete or In Progress.
JOB RESULTS
| Job / Project Name | Row Inputs | Revised Contract | Est. Gross Profit | Est. Gross Margin % | Act. / Current Gross Profit | Act. / Current Margin % | Cost Variance $ | Cost Variance % | Margin Variance (pp) | Basis of the result shown
| Harbourview Retail Fit-Out | Complete | 517000 | 119000 | 23.02% | 99000 | 19.15% | 20000 | 5.025% | -3.8685 | Actual result — this job is marked complete.
| Cedar Ridge Multi-Unit Renovation | Complete | 910500 | 204500 | 22.46% | 231500 | 25.43% | -27000 | -3.824% | 2.9654 | Actual result — this job is marked complete.
| Riverbend Warehouse Expansion | Complete | 1316000 | 292000 | 22.19% | 464500 | 35.3% | -172500 | -16.85% | 13.1079 | Current / projected from the costs entered so far — this may change.
| Northgate Roof Replacement | Complete | 168000 | 35500 | 21.13% | 25300 | 15.06% | 10200 | 7.698% | -6.0714 | Actual result — this job is marked complete.
| Willowbrook Tenant Improvements | Complete | 360900 | 93900 | 26.02% | 106100 | 29.4% | -12200 | -4.569% | 3.3804 | Actual result — this job is marked complete.
| Sunnyside Mechanical Upgrade | Complete | 596000 | 109000 | 18.29% | 262500 | 44.04% | -153500 | -31.52% | 25.755 | Current / projected from the costs entered so far — this may change.
For a job marked Complete, the result is the actual outcome based on the costs entered. For a job In Progress, it is a current or projected figure based only on the costs entered so far and may change as further costs are incurred or the contract value changes. This workbook does not perform percentage-of-completion, work-in-progress or revenue-recognition accounting.
PORTFOLIO TOTALS ALL JOBS ENTERED
| Measure |  |  |  | Value |  | Basis
| Jobs Entered |  |  |  | 6 |  | Rows where every required field is entered.
| Total Revised Contract Value |  |  |  | 3868400 |  | Original contract value plus approved change orders, across the jobs entered.
| Total Estimated Direct Costs |  |  |  | 3014500 |  | The four estimated cost lines, across the jobs entered.
| Total Estimated Gross Profit |  |  |  | 853900 |  | Total revised contract value less total estimated direct costs.
| Weighted Estimated Gross Margin % |  |  |  | 22.07% |  | Total estimated gross profit divided by total revised contract value.
This block includes every job row whose required fields are entered, whether the job is complete or in progress. It is a view of the estimated economics of the work entered, not a forecast of results.
ESTIMATE VERSUS ACTUAL COMPLETED JOBS ONLY
| Measure |  |  |  | Value |  | Basis
| Completed Jobs Entered |  |  |  | 4 |  | Jobs marked Complete with every required field entered.
| Total Revised Contract Value |  |  |  | 1956400 |  | Contract value of the completed jobs entered.
| Total Estimated Direct Costs |  |  |  | 1503500 |  | Estimated cost of the same completed jobs.
| Total Actual Direct Costs |  |  |  | 1494500 |  | Actual cost of the same completed jobs.
| Total Estimated Gross Profit |  |  |  | 452900 |  | Contract value less estimated cost, for completed jobs.
| Total Actual Gross Profit |  |  |  | 461900 |  | Contract value less actual cost, for completed jobs.
| Weighted Estimated Gross Margin % |  |  |  | 23.15% |  | Total estimated gross profit divided by total contract value — not an average of job margins.
| Weighted Actual Gross Margin % |  |  |  | 23.61% |  | Total actual gross profit divided by total contract value.
| Total Cost Variance $ |  |  |  | -9000 |  | Actual cost less estimated cost. Positive means costs above estimate.
| Weighted Margin Variance (pp) |  |  |  | 0.46003 |  | Weighted actual margin less weighted estimated margin, in percentage points.
Jobs in progress are deliberately excluded from this comparison. Their costs are not final, so including them would compare a complete estimate against an incomplete actual and overstate margin. Individual in-progress jobs are still shown in the results table above.
NEUTRAL OBSERVATIONS
| Observation |  |  |  | Job / Project | [5 empty] | Value |  | What the value is
| Largest Job by Revised Contract Value |  |  |  | Riverbend Warehouse Expansion | [5 empty] | 1316000 |  | revised contract value
| Largest Favourable Cost Variance |  |  |  | Cedar Ridge Multi-Unit Renovation | [5 empty] | -27000 |  | cost below estimate
| Largest Cost Overrun |  |  |  | Harbourview Retail Fit-Out | [5 empty] | 20000 |  | cost above estimate
| Largest Margin Improvement vs Estimate |  |  |  | Willowbrook Tenant Improvements | [5 empty] | 3.3804 |  | margin above estimate
| Largest Margin Decline vs Estimate |  |  |  | Northgate Roof Replacement | [5 empty] | -6.0714 |  | margin below estimate
These observations identify where the largest differences sit among the jobs entered. They do not say that any job is good or bad — a variance is a question to investigate, not a conclusion. Contract-value ranking covers every job entered; the variance rankings cover completed jobs only, and no job is named as favourable or unfavourable when the actual variance is zero.
Vertex Strategic Finance ¦ FICTIONAL EXAMPLE DATA — FOR DEMONSTRATION ONLY. Replace these jobs with your own.

## KPI ANALYSIS
VERTEX STRATEGIC FINANCE
KPI Analysis | [5 empty] | FICTIONAL EXAMPLE DATA — FOR DEMONSTRATION ONLY
Current reporting period against your prior month and your own targets, with a twelve-month trend.
Every figure here is calculated from the MONTHLY INPUTS and JOB PERFORMANCE tabs and compared with the targets you set on the KPI TARGETS tab. Targets are your own planning goals — this workbook publishes no contractor benchmarks and recommends no level for any measure.
CURRENT REPORTING PERIOD
Reporting month: Dec 2025 Marked complete. Profitability inputs: complete.
REVENUE AND PROFITABILITY
| KPI | Current | Prior | Change | Your Target | Status |  | How this is read
| Total Revenue | 518100 | 570800 | -52700 | 600000 | Below Target |  | Compared with the monthly revenue target you entered. Revenue is not cash.
| Revenue Growth % | -9.233% | — | — | — | Context Dependent |  | Growth against the prior month. Contract work is lumpy — a fall is not automatically bad.
| Gross Profit | 133200 | 142100 | -8900 | — | Monitor |  | Revenue less the direct job costs entered. Not net income.
| Gross Margin % | 25.71% | 24.89% | 0.81444 | 24% | Above Target |  | Compared with your own gross margin target, not an industry figure.
| Operating Profit | 21820 | 35520 | -13700 | — | Monitor |  | Gross profit less overhead entered. Owner draws are not deducted.
| Operating Margin % | 4.212% | 6.223% | -2.0113 | 6% | Below Target |  | Compared with your own operating margin target.
COST STRUCTURE (SHARE OF REVENUE)
| KPI | Current | Prior | Change | Your Target | Status |  | How this is read
| Direct Labour % of Revenue | 23.1% | 23.06% | 0.048287 | 23% | Above Target |  | Self-performed work raises this and lowers the subcontractor share.
| Subcontractor % of Revenue | 26.08% | 26.66% | -0.58828 | 28% | Below Target |  | Subcontracted work raises this and lowers the direct labour share.
| Materials % of Revenue | 20.21% | 20.36% | -0.14894 | 20% | Above Target |  | Moves with job mix as well as with material prices.
| Total Direct Job Cost % of Revenue | 74.29% | 75.11% | -0.81444 | 76% | Below Target |  | The complement of gross margin: this share plus gross margin equals 100%.
| Overhead % of Revenue | 21.5% | 18.67% | 2.8257 | 18% | Above Target |  | Mostly fixed cost over a variable revenue base, so it rises in quieter months.
Cost shares are reported against your own targets. There is no universally correct split between self-performed labour, subcontractors and materials — it depends on how you choose to deliver work. A share above your target is a question to investigate, not a fault.
CASH AND WORKING CAPITAL
| KPI | Current | Prior | Change | Your Target | Status |  | How this is read
| Cash Balance | 487000 | 458000 | 29000 | 350000 | Above Minimum |  | Compared with the minimum cash level you entered — your figure, not a recommended one.
| Accounts Receivable | 903000 | 1033000 | -130000 | — | Monitor |  | The balance owed to you at month end, as entered.
| Accounts Payable | 470000 | 537000 | -67000 | — | Monitor |  | The balance you owe at month end, as entered.
| Current Ratio | 1.789 | 1.7407 | 0.048357 | — | Context Dependent |  | Current assets divided by current liabilities. N/M where current liabilities are zero.
| Approximate A/R Days | 52.9844 | 55.0161 | -2.0318 | 55 | Below Target |  | Receivables divided by the month's revenue, times 30.4 days. A single-month approximation.
| Cash Coverage (months) | 0.9813 | 0.85563 | 0.12567 | 0.75 | Above Target |  | Cash divided by the month's direct job costs plus overhead. No level is universally right.
JOB AND OPERATING ACTIVITY
| KPI | Current | Prior | Change | Your Target | Status |  | How this is read
| Jobs Completed | 4 | 5 | -1 | — | Monitor |  | Count entered for the reporting month.
| Jobs in Progress | 7 | 7 | 0 | — | Context Dependent |  | More jobs open is neither good nor bad on its own — it depends on capacity.
| Backlog | 1595000 | 1445000 | 150000 | 1500000 | Above Target |  | Contracted work not yet revenue. It is not cash and not guaranteed profit.
| Approved Change Orders | 41200 | 14600 | 26600 | — | Context Dependent |  | Approved scope added in the month. A large figure is worth understanding, not judging.
| Quote Conversion % | 44.44% | 37.5% | 6.9444 | — | Context Dependent |  | Optional. A lower conversion rate can reflect deliberate selectivity on which work to bid.
JOB PERFORMANCE FROM THE JOB PERFORMANCE TAB
| KPI | Current | Prior | Change | Your Target | Status |  | How this is read
| Weighted Estimated Job Margin | 23.15% | — | — | — | Monitor |  | Completed jobs entered: total estimated gross profit over total contract value.
| Weighted Actual Job Margin | 23.61% | — | — | — | Monitor |  | Completed jobs entered: total actual gross profit over total contract value.
| Job Margin Variance (pp) | 0.46003 | — | — | 0 | Above Target |  | Actual weighted margin less estimated weighted margin. Positive is above estimate.
| Total Cost Variance $ | -9000 | — | — | — | Monitor |  | Actual cost less estimated cost on completed jobs. Positive means costs above estimate.
Statuses compare your result with the target you entered, or report the measure where no single direction is correct. Above Target and Below Target are factual statements about your own target — they are not judgements about your business, and this workbook never states that a level is healthy.
TWELVE-MONTH TREND
| Measure | Jan 2025 | Feb 2025 | Mar 2025 | Apr 2025 | May 2025 | Jun 2025 | Jul 2025 | Aug 2025 | Sep 2025 | Oct 2025 | Nov 2025 | Dec 2025
| Total Revenue | 446500 | 416800 | 501200 | 582100 | 670400 | 730200 | 783800 | 757100 | 697600 | 642900 | 570800 | 518100
| Gross Profit | 115200 | 105000 | 123200 | 136200 | 148100 | 150400 | 152000 | 157400 | 155600 | 151700 | 142100 | 133200
| Gross Margin % | 25.8% | 25.19% | 24.58% | 23.4% | 22.09% | 20.6% | 19.39% | 20.79% | 22.31% | 23.6% | 24.89% | 25.71%
| Operating Profit | 13650 | -850 | 18150 | 28220 | 36220 | 36720 | 36320 | 43320 | 43470 | 42970 | 35520 | 21820
| Operating Margin % | 3.057% | -0.2039% | 3.621% | 4.848% | 5.403% | 5.029% | 4.634% | 5.722% | 6.231% | 6.684% | 6.223% | 4.212%
| Ending Cash | 248000 | 226000 | 214000 | 209000 | 198000 | 221000 | 256000 | 312000 | 368000 | 421000 | 458000 | 487000
Blank cells in the trend mean the required inputs for that month have not been entered. A month with zero revenue that is genuinely complete shows as zero, not as a blank.
Vertex Strategic Finance ¦ FICTIONAL EXAMPLE DATA — FOR DEMONSTRATION ONLY. Targets are user-defined planning goals, not industry benchmarks or recommendations.

## KPI TARGETS
VERTEX STRATEGIC FINANCE
KPI Targets |  |  | FICTIONAL EXAMPLE DATA — FOR DEMONSTRATION ONLY
Your own planning goals. This workbook publishes no contractor benchmarks.
Every target below is yours to set. Enter the level you are planning to, not a level anyone told you is normal. Leave a target blank and the matching KPI simply reads Set Target — nothing else is affected. Zero targets are valid, and negative targets are accepted where they make mathematical sense.
FICTIONAL EXAMPLE TARGET — NOT AN INDUSTRY BENCHMARK OR RECOMMENDATION. Every figure in the shaded column is example data for a fictional contractor. Replace each one with your own target.
YOUR TARGETS
| Target | Your Figure |  | Notes
| Monthly Revenue Target | 600000 |  | The monthly revenue level you are planning to.
| Gross Margin % Target | 24% |  | Your own gross margin goal, after direct job costs.
| Operating Margin % Target | 6% |  | Your own operating margin goal, after overhead.
| Direct Labour % of Revenue Target | 23% |  | Depends on how much work you self-perform. There is no correct level.
| Subcontractor % of Revenue Target | 28% |  | Moves in the opposite direction to the direct labour share.
| Materials % of Revenue Target | 20% |  | Depends on trade, job mix and how materials are procured.
| Total Direct Job Cost % of Revenue Target | 76% |  | The complement of your gross margin target.
| Overhead % of Revenue Target | 18% |  | Overhead is largely fixed, so this share moves with revenue.
| A/R Days Target | 55 |  | The average collection period you are working towards.
| Minimum Desired Cash | 350000 |  | The cash floor you want to hold. Your figure, not a recommended reserve.
| Cash Coverage Target (months) | 0.75 |  | Months of direct job cost plus overhead you want cash to cover.
| Backlog Target (optional) | 1500000 |  | Optional. Only useful alongside your own view of capacity.
| Job Margin Variance Target (pp) | 0 |  | Percentage points of actual margin against estimate. Enter 1.5 for 1.5 pp.
Targets in this workbook are user-defined planning goals, not industry benchmarks or recommendations. Vertex Strategic Finance publishes no target margin, cost share, collection period, cash level or backlog level for any trade, and this workbook does not invent one. A result above or below a target is a statement about your own figure and nothing more.
Targets entered: 13 of 13. Every comparison on the KPI ANALYSIS tab is live.
Vertex Strategic Finance ¦ FICTIONAL EXAMPLE DATA — FOR DEMONSTRATION ONLY. Replace every target with your own.

## WORKING CAPITAL
VERTEX STRATEGIC FINANCE
Working Capital | [5 empty] | FICTIONAL EXAMPLE DATA — FOR DEMONSTRATION ONLY
Cash, receivables, payables and the timing behind them.
These figures come from the cash and working capital lines on the MONTHLY INPUTS tab and use the same statuses as the KPI ANALYSIS tab, so the two always agree.
CURRENT REPORTING PERIOD
Reporting month: Dec 2025 Marked complete. Profitability inputs: complete.
POSITION
| Measure | Current | Prior | Change | Your Target | Status |  | How this is read
| Cash | 487000 | 458000 | 29000 | 350000 | Above Minimum |  | Compared with the minimum cash you entered on the KPI TARGETS tab.
| Accounts Receivable | 903000 | 1033000 | -130000 | — | Monitor |  | Owed to you at month end, as entered.
| Accounts Payable | 470000 | 537000 | -67000 | — | Monitor |  | Owed by you at month end, as entered.
| Net Working Capital | 632000 | 654000 | -22000 | — | Context Dependent |  | Current assets less current liabilities, as entered.
| Current Ratio | 1.789 | 1.7407 | 0.048357 | — | Context Dependent |  | Current assets divided by current liabilities. N/M where current liabilities are zero.
| Approximate A/R Days | 52.9844 | 55.0161 | -2.0318 | 55 | Below Target |  | Receivables divided by the month's revenue, times 30.4 days.
| Cash Coverage (months) | 0.9813 | 0.85563 | 0.12567 | 0.75 | Above Target |  | Cash divided by the month's direct job costs plus overhead.
No level of cash, coverage or current ratio is universally healthy. Each is compared only with the figure you entered on the KPI TARGETS tab, and where you have entered none the status reads Set Target.
TWELVE-MONTH MOVEMENT
| Measure | Jan 2025 | Feb 2025 | Mar 2025 | Apr 2025 | May 2025 | Jun 2025 | Jul 2025 | Aug 2025 | Sep 2025 | Oct 2025 | Nov 2025 | Dec 2025
| Ending Cash | 248000 | 226000 | 214000 | 209000 | 198000 | 221000 | 256000 | 312000 | 368000 | 421000 | 458000 | 487000
| Accounts Receivable | 764000 | 740000 | 940000 | 1168000 | 1411000 | 1633000 | 1831000 | 1718000 | 1469000 | 1248000 | 1033000 | 903000
| Accounts Payable | 397000 | 385000 | 489000 | 607000 | 734000 | 849000 | 952000 | 893000 | 764000 | 649000 | 537000 | 470000
| Net Working Capital | 339000 | 313000 | 379000 | 455000 | 538000 | 647000 | 763000 | 773000 | 730000 | 698000 | 654000 | 632000
| Current Ratio | 1.4741 | 1.453 | 1.4616 | 1.4667 | 1.4753 | 1.5082 | 1.5477 | 1.5852 | 1.6266 | 1.6823 | 1.7407 | 1.789
| Approximate A/R Days | 52.017 | 53.9731 | 57.0152 | 60.9985 | 63.9833 | 67.9858 | 71.0161 | 68.9832 | 64.0161 | 59.0126 | 55.0161 | 52.9844
| Cash Coverage (months) | 0.57295 | 0.54112 | 0.44302 | 0.37734 | 0.31221 | 0.31868 | 0.34248 | 0.43711 | 0.56258 | 0.70175 | 0.85563 | 0.9813
A blank month means the inputs that measure needs have not been entered for that month. It does not mean zero.
WHY A PROFITABLE MONTH MAY NOT FEEL LIKE ONE
A profitable job or a profitable month does not necessarily produce immediate cash. The timing of customer collections, supplier payments, payroll, materials, deposits, retainage or holdbacks where they apply, equipment purchases and debt payments can all affect cash independently of profit. This workbook reports the balances you enter; it does not model statutory holdback or retainage requirements, which vary by jurisdiction and by contract, and it offers no construction-law or legal advice.
Vertex Strategic Finance ¦ FICTIONAL EXAMPLE DATA — FOR DEMONSTRATION ONLY. Revenue is not cash, and profit is not cash.

## ACTION PLAN
VERTEX STRATEGIC FINANCE
Action Plan |  | FICTIONAL EXAMPLE DATA — FOR DEMONSTRATION ONLY
Questions worth investigating, drawn from your own figures.
These are questions, not instructions. Each one is raised by the statuses on the KPI ANALYSIS tab, so what appears here always matches what that tab reports. Where information is missing, the question asks you to complete the inputs rather than drawing a conclusion from a gap.
QUESTIONS FOR THIS REPORTING PERIOD
| Area | Question worth investigating
| Gross Margin | Gross margin is 25.7%. Which jobs and which pricing decisions are holding it there, and are those conditions repeatable next period?
| Job Margin vs Estimate | Actual weighted job margin is 0.5 percentage points against estimate. Which estimating assumptions proved accurate, and do they hold for the work now being quoted?
| Collections | Approximate A/R days are 53.0. Which billing and collection practices are keeping them there, and are they applied consistently across jobs?
| Backlog and Capacity | Backlog moved +10.4% to $1,595,000. Does that align with available labour, subcontractor capacity and expected project timing?
| Materials and Change Orders | Approved change orders were $41,200 in the period. Are they being billed and reflected in project forecasts promptly?
These questions are prompts for your own review. They are not advice, and they do not say that anything is wrong. A variance is a question to investigate, and the answer often lies in job mix, timing or a deliberate decision you already made.
WHAT THIS SECTION DOES NOT DO
This section does not tell you what to charge, who to hire, how much cash to hold or what margin to target. It has no view on what is normal for your trade, your region or your size of business. Where an input is missing it asks you to complete it rather than inferring a problem, because a blank cell is missing information and not a zero.
Vertex Strategic Finance ¦ FICTIONAL EXAMPLE DATA — FOR DEMONSTRATION ONLY. Questions only — not accounting, tax, legal or financial advice.

## EXECUTIVE DASHBOARD
VERTEX STRATEGIC FINANCE
Contractor KPI Dashboard |  |  |  |  | FICTIONAL EXAMPLE DATA — FOR DEMONSTRATION ONLY
Revenue, margin, cash and job performance for the reporting month — all figures calculated from your own inputs.
Chart 3 feed — direct cost composition, reporting month
| REVENUE |  | GROSS MARGIN | OPERATING PROFIT |  | OPERATING MARGIN | Direct Labour | 119700
| 518100 |  | 25.71% | 21820 |  | 4.212% | Subcontractors | 135100
| reporting month Dec 2025 |  | your target 24.0% | after the overhead entered |  | your target 6.0% | Materials | 104700
[7 empty] | Other Direct | 25400
| CASH |  | APPROXIMATE A/R DAYS | BACKLOG |  | JOB MARGIN VARIANCE
| 487000 |  | 52.9844 | 1595000 |  | 0.46003
| your minimum $350,000 |  | your target 55.0 days | contracted work not yet revenue |  | completed jobs, actual less estimate
| 1. Revenue and Gross Profit by Month |  |  | 2. Gross Margin and Operating Margin by Month
| 3. Direct Cost Composition — Reporting Month |  |  | 4. Estimated vs Actual Job Margin — Completed Jobs
CONTRACTOR FINANCIAL PULSE
| ▪ | Gross margin is 25.7%, at or above your entered target of 24.0%, and 0.8 percentage points above the prior month.
| ▪ | Operating profit is $21,820 on revenue of $518,100, an operating margin of 4.2%. Owner draws are not deducted from this figure.
| ▪ | Across the completed jobs entered, actual weighted job margin is 0.5 percentage points above the estimated weighted margin of 23.1%.
| ▪ | Of revenue in the reporting month, direct labour was 23.1%, subcontractors 26.1% and materials 20.2%. How work is split between self-performed and subcontracted labour moves these shares.
| ▪ | Approximate A/R days are 53.0, 2.0 days lower than the prior month. Cash of $487,000 is above the minimum you entered.
Revenue $518,100 ¦ Gross margin 25.7% ¦ Operating margin 4.2% ¦ Cash $487,000 ¦ A/R days 53.0.
Every figure on this dashboard is calculated from the information you entered. Targets are your own planning goals: this workbook applies no contractor benchmark and makes no recommendation about margin, cost share, collection period, cash level or backlog. Gross profit is not net income, backlog is not cash or guaranteed profit, and revenue is not cash. Results for jobs in progress are based only on the costs entered so far and may change. Nothing here constitutes accounting, tax, legal, construction-law, investment or financial advice, nor assurance or a professional opinion on any business. All figures shown are FICTIONAL EXAMPLE DATA.
Vertex Strategic Finance ¦ CPA-Led Accounting & Advisory for Owner-Led Businesses ¦ www.vertexstrategicfinance.ca